## RFI form
REQUEST FOR INFORMATION (RFI)
PROJECT AND ROUTING
Project | Project no.
RFI no. | Date sent
To (architect / engineer) | From (contractor)
Response needed by | Priority
REFERENCE
Subject | Discipline
Drawing / sheet | Spec section
Location | Attachments
QUESTION (one question per RFI; say what the documents show and why it does not work)
SUGGESTED SOLUTION (optional, from the contractor)
POSSIBLE IMPACT
Cost impact | Schedule impact
RESPONSE (by the architect or engineer)
Answered by | Date answered
An RFI response clarifies the contract documents. If it changes cost or time, the change must go through a change order or an ASI, not this form.
Free RFI template by AIBIMTool, aibimtool.com/blog/rfi-construction. Public domain (CC0).

## RFI log
RFI no. | Subject | Discipline | Drawing / spec ref. | Sent to | Date sent | Needed by | Date answered | Days open | Status | Cost impact | Schedule impact | Linked ASI / CO | Notes
RFI-045 | Door D2.14 hardware set not in schedule | Architectural | A-601, 08 71 00 | Northlight | 2026-10-28 | 2026-11-04 | 2026-11-03 |  | Closed | No | No
RFI-046 | Footing F7 depth vs. existing sewer | Structural | S-101, C-201 | Example Engineers | 2026-10-30 | 2026-11-06 |  |  | Open | TBD | TBD |  | Survey sent 10-31
RFI-047 | Beam B-12 clashes with supply duct at C/4 | Structural / mech. | S-201, M-201 | Northlight | 2026-11-04 | 2026-11-11 | 2026-11-06 |  | Answered | No | No | ASI-012
Free RFI template by AIBIMTool, aibimtool.com/blog/rfi-construction. Public domain (CC0).
Formulas:
Days open = IF([Date sent]="","",IF([Date answered]<>"",[Date answered]-[Date sent],TODAY()-[Date sent]))